## Sheet1
#	Type	Priority	Status	Title	Description and comments	Estimated [h]	Actual [h]	Who	Date created	Date closed
	feat	3 [high]	OPEN
	fix	2 [medium]	WORK-IN-PROGRESS
	docs	1 [low]	CLOSED
	style
	refactor
	perf
	test
	chore
	build
	ci

1	feat	3 [high]	OPEN	Confirmations and -y options
2	feat	3 [high]	OPEN	How to have a single point of truth for version.
3	feat	2 [medium]	OPEN	Templating or cookie cutter for pyproject.toml
4	fix	3 [high]	CLOSED	Flawless pep8, linting and format of buildingbits.py	Should not pollute the output of other projects !	1	1	GF	07/10/21	07/10/21
5	feat	2 [medium]	CLOSED	Header for buildingbits.py, downloaded files / And generated files		2	1	GF	11/10/21	11/10/21
6	feat	3 [high]	CLOSED	miniconda dockerfile bit should be base on Python 3.9		1	1	GF	07/12/21	07/12/21
7	fix	3 [high]	CLOSED	MD5 sum of miniconda install script	8c69f65a4ae27fb41df0fe552b4a8a3b	1	1	GF	07/12/21	07/12/21
8	feat	2 [medium]	OPEN	--cov options for pytest (tests_ target)	--cov=<project>.<package> for each package	4		GF	7/12/2021
9	feat	2 [medium]	CLOSED	C compiling tools		2	1	GF	7/12/2021	20/12/2021
10	feat	2 [medium]	CLOSED	FORTRAN compiling tools	gfortran	2	1	GF	7/12/2021	20/12/2021
11	feat	2 [medium]	OPEN	Julia		4		GF	7/12/2021
12	feat	2 [medium]	CLOSED	Wx	Required libraries to build wx (and wxPython)	4	1	GF	7/12/2021	20/12/2021
13	feat	3 [high]	CLOSED	Separate TZDATA setup	it is actually in dockerfilebits_common_infrastructure → remove / Update impacted dockerfile templates	4	1	GF	7/12/2021	20/12/2021
14	feat	3 [high]	CLOSED	C++ compiling tools		4	1	GF	20/12/2021	20/12/2021
15	fix	3 [high]	CLOSED	Typo in SUPPORTED_DOCKERFILE_KEYS		1	1	GF	20/12/2021	20/12/2021
16	fix	3 [high]	CLOSED	Remove . In bits names	Causes problems with jinja2	2	1	GF	20/12/2021	20/12/2021
17	feat	2 [medium]	OPEN	Aoc-utils Dockerfilebit		2		GF	21/12/2021
18	feat	2 [medium]	OPEN	Aoc-xchange Dockerfilebit		2		GF	21/12/2021
19	fix	3 [high]	CLOSED	No PyQt for OCC	Because of XCB and other problems. Wx should be the default backend.	1	1	GF	21/12/2021	21/12/2021