## Sheet1
#	Type	Priority	Status	Title	Description and comments	Estimated [h]	Actual [h]	Who	Date created	Date closed
	feat	3 [high]	OPEN
	fix	2 [medium]	WORK-IN-PROGRESS
	docs	1 [low]	CLOSED
	style
	refactor
	perf
	test
	chore
	build
	ci

1	feat	3 [high]	OPEN	Confirmations and -y options
2	feat	3 [high]	OPEN	How to have a single point of truth for version.
3	feat	2 [medium]	OPEN	Templating or cookie cutter for pyproject.toml
4	fix	3 [high]	CLOSED	Flawless pep8, linting and format of buildingbits.py	Should not pollute the output of other projects !	1	1	GF	07/10/21	07/10/21